## focus_planner_config (hidden)
planid | 0wnpDRazhkmmFqbDTGyrj2UACGYj
bucketid | bN2qlVl-f0Kxo8IzpYxZp2UAMvGr

## Cover
Count of Task | Column Labels
Row Labels | Completed | In Progress | Not started | Grand Total | Row Labels | Count of Task
General Bucket | 1 | 1 | 8 | 10 | Completed | 1
Grand Total | 1 | 1 | 8 | 10 | In Progress | 1
[5 empty] | Not started | 8
[5 empty] | Grand Total | 10
Focus Report for General Bucket
10/24/2019

## Focus Task Data
Task | Owner | Email | Bucket | Progress | Due Date | Completed Date | Completed By | Created Date | Task Id
Door name plate | Tom Jebo | tomjebo@jebosoft.onmicrosoft.com | General Bucket | Not started | 10/31/2019 |  |  | 10/24/2019 | LOH49GDkXkyqpqQ6EE9mL2UAE2Zu
Door hinge lubricate | Will Gregg | grjoh@jebosoft.onmicrosoft.com | General Bucket | Not started | 10/23/2019 |  |  | 10/16/2019 | sWiynBLGbkGS4lfLSqb81WUAPADR
Plane door fitting | Tom Jebo | tomjebo@jebosoft.onmicrosoft.com | General Bucket | Completed | 10/23/2019 | 10/24/2019 | Tom Jebo | 10/16/2019 | Jy--sr5EiEacxCmeSAqey2UAI1Z1
Pipe fitting breach | Tom Jebo | tomjebo@jebosoft.onmicrosoft.com | General Bucket | Not started | 10/16/2019 |  |  | 10/16/2019 | Jf7MUpvBwkeXxAMKZsbiPGUADxFo
Temp control adjustment | Tom Jebo | tomjebo@jebosoft.onmicrosoft.com | General Bucket | Not started | 10/16/2019 |  |  | 10/16/2019 | uXAm1_q31kyEfZsAE8Tlp2UACBDI
Seal leaking joint | Tom Jebo | tomjebo@jebosoft.onmicrosoft.com | General Bucket | Not started | 10/16/2019 |  |  | 10/16/2019 | kk4v-h0O8USSkSmFkWaWOmUAKxWt
Missing part | Tom Jebo | tomjebo@jebosoft.onmicrosoft.com | General Bucket | Not started | 10/23/2019 |  |  | 10/16/2019 | mb2Qr1gWXE6csxpwJJ6VVmUAOfhy
Part replacement | Tom Jebo | tomjebo@jebosoft.onmicrosoft.com | General Bucket | Not started | 10/16/2019 |  |  | 10/16/2019 | xZ16DnsJBk68gKYvfA6nvWUALkFs
Inspect housing | Tom Jebo | tomjebo@jebosoft.onmicrosoft.com | General Bucket | Not started | 10/16/2019 |  |  | 10/16/2019 | pmN01K_Qj0GSwhuq1rjc7mUAHCiV
Inspect case for control | Tom Jebo | tomjebo@jebosoft.onmicrosoft.com | General Bucket | In Progress | 10/16/2019 | 10/24/2019 | Tom Jebo | 10/16/2019 | tEZK3oGsukWVbcRYnHhGJWUAADap
Weld joint | Tom Jebo | tomjebo@jebosoft.onmicrosoft.com | General Bucket | In Progress | 10/16/2019 | 10/24/2019 | Tom Jebo | 10/16/2019 | R2mei2W-_US75rtnkZeO5mUALU4d